Implementation Plan for Needs Identified in the Community Health Needs Assessment for 
Presentation Medical Center

FY 2020-2021

Updates noted in Red

Covered Facilities: Presentation Medical Center and Rolette County Public Health

Community Health Needs Assessment: A Community Health Needs Assessment (“CHNA”) was performed in Summer of 2019 in collaboration with Rolette County Public Health to determine the most pressing health needs of Rolette County area.

Implementation Plan Goals: The Board of Presentation Medical Center has determined that the following health needs identified in the CHNA should be addressed through the implementation strategy noted for each such need:

- Ability to retain primary care providers (MD, DO, NP, PA) –

Specific Needs Identified in CHNA:

- Ensure Presentation Medical Center has a stable roster of primary care providers.

- Key Objectives:

  - Recruit primary care providers to meet the needs of the Rolette County community

  - Increase the retention rate of primary care providers to improve the continuity of care in the Rolette County community.

  - Implementation Strategies:

  - Expand Presentation Medical Center’s roster of primary care providers providers in Presentation Clinic.

Goals:

    - Expand the Presentation Medical Center’s clinic foot print to allow for more primary care provider capacity.

    - Obtain a total of 5 full-time primary care providers working in Presentation Medical Center’s clinic (Presentation Medical Center currently employs 3 primary care providers in its clinic, and has 1 NP committed to employment following her graduation).

  - Maximize HRSA student loan repayment opportunities and 3RNet to recruit new primary care providers to Rolette County.

Goals:

- Employ a 5th primary care provider after the PMC’s clinic footprint has expanded.

12/1/2020

PMC currently has 5 primary care providers in its rural health clinic (1 MD, 3 NPs, and 1 PA).

  - Utilize the Medical Provider Recruitment/Retention Plan, developed in 2018, to recruit and retain primary care providers.

Goals:

- Increase the long-term retention (greater than 3 years) rate for primary care providers employed by Presentation Medical Center (PMC’s current long-term retention rate is 0).

12/1/2020

PMC’s long-term retention rate remains at 0.  However, PMC has engaged 2 NPs for scholarships to extend their commitment to PMC.

2. Youth drug use and abuse (including prescription drugs)

Specific Needs Identified in CHNA:

- Both youth and adult drug use and abuse were specific areas of concern noted in the 2019 Rolette County CHNA.

- Key Objectives:

  - Obtain meaningful data regarding drug use and abuse

  - Increase the number of patients in Presentation Medical Center’s Medication Assisted Treatment program

  - Implementation Strategies:

  - Gather key players (i.e. local governmental agencies, local health agencies) to share useful data.

The goals:

- Obtain “buy in” from local agencies

- Develop a dashboard to be shared between all local agencies

12/1/2020

This effort between local agencies has been hampered due to the COVID-19 Pandemic.

  - Expand Presentation Medical Center’s Medication Assisted Treatment program.

The goals:

- Increase the number of MAT patients in PMC’s MAT program

- Increase the number of providers able to participate in the MAT program

12/1/2020

PMC has expanded the number of MAT patients.  PMC has also been hosting Narcotics Anonymous, when appropriate,e as COVID-19 allows.  PMC has also partnered with the TMBCI to promote diversity in recovery, spearheaded by Maryn Young, FNP-BC

Other Needs Identified in the CHNA but Not Addressed in this Plan – Each of the health needs listed below is important and is being addressed by numerous programs and initiatives operated by Presentation Medical Center, and/or other community partners of Presentation Medical Center. However, Presentation Medical Center will not address the following health needs identified in the CHNA as part of this Implementation Plan due to limited resources and the need to allocate significant resources to the two priority health needs identified above.

  - Adult Obesity